## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name: | UI + API Hybrid Automation – ExpandTesting Notes App
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | V.Yashwanth Kumar
Approved By:
SCOPE
Features to be Tested:
1.User Login and Validation Functionality
2.User Login and Validation Functionality
3.Notes API Testing (GET and DELETE)
4.Hybrid UI + API Synchronization
5.Logout Functionality
TESTING TYPE
Functional Testing | ☑
Regression Testing | ☑
Integration Testing | ☑
UAT | ☐
TEST ENVIRONMENT
Environment: | Dev / QA / Staging / Production
Browser/OS: | Chrome/Windows 11
TIMELINE
Start Date: | 2026-05-04
End Date: | 2026-05-07
RESOURCES
QA Lead: | V.Yashwanth Kumar
QA Resources: | Selenium, Pytest, Postman, Allure Report
Test Data Provider: | Manual and API Test Data
RISKS & ASSUMPTIONS
Risks: | API downtime or internet instability may affect execution
Assumptions: | Application and API services are available during testing

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | User Login | Verify user can login with valid credentials | Registered user account exists
SC-002 | Invalid Login Validation | Verify invalid login handling | Login page accessible
SC-003 | Create Note | Verify note creation with valid details | User logged in
SC-004 | Instant Note Display | Verify created note appears instantly | User logged in
SC-005 | Validation Handling | Verify validation for empty fields and duplicate notes | User logged in
SC-006 | API GET Notes | Verify GET notes API response | Valid API token
SC-007 | API Delete Notes | Verify DELETE note API functionality | Existing note available
SC-008 | Hybrid UI + API | Verify synchronization between UI and API | UI and API accessible
SC-009 | API Performance Validation | Verify API response time performance | API endpoint accessible
SC-009 | API POST Note | Verify note creation through API | Valid API token available
SC-010 | Empty Note Validation | Verify empty note is not accepted | User logged in
SC-011 | Invalid Token Handling | Verify API response for invalid token | Invalid or expired API token used
SC-012 | UI and API Data Consistency | Verify created note matches in UI and API | UI and API accessible

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Actual Result | Priority | Status
TC-001 | SC-001 | Login with valid credentials | User account exists | 1.Open app 2.Click Login 3.Enter valid credentials 4.Click Login | User logged in successfully | User logged in successfully | High | Pass
TC-002 | SC-002 | Login with invalid credentials | Login page available | 1.Enter invalid credentials 2.Click Login | Error message displayed | Error message displayed | High | Pass
TC-003 | SC-003 | Create note with valid details | User logged in | 1.Click Add Note 2.Enter title 3.Enter description 4.Click Create | Note created successfully | Note created successfully | High | Pass
TC-004 | SC-005 | Create note with empty title | User logged in | 1.Click Add Note 2.Leave title empty 3.Click Create | Validation message displayed | Validation message displayed | Medium | Pass
TC-005 | SC-005 | Duplicate note creation handling | User logged in | 1.Create note 2.Create same note again | Duplicate error displayed | Duplicate error displayed | Medium | Pass
TC-006 | SC-005 | Invalid category handling | User logged in | 1.Try invalid category data | System handles invalid category | System handled invalid category | Low | Pass
TC-007 | SC-006 | GET notes API validation | API token available | 1.Send GET /notes request | API returns notes list | API returned notes list | High | Pass
TC-008 | SC-007 | DELETE note API validation | Existing note available | 1.Send DELETE request | Note deleted successfully | Note deleted successfully | High | Pass
TC-009 | SC-006 | API invalid token validation | API endpoint accessible | 1.Send request with invalid token | Unauthorized response returned | Unauthorized response returned | High | Pass
TC-010 | SC-006 | API invalid endpoint validation | API endpoint accessible | 1.Send request to invalid endpoint | 404 response returned | 404 response returned | Medium | Pass
TC-011 | SC-006 | API missing fields validation | API endpoint accessible | 1.Send request with missing fields | Validation error displayed | Validation error displayed | Medium | Pass
TC-012 | SC-004 | Verify note appears instantly | User logged in | 1.Create note 2.Check notes list | New note appears instantly | New note appeared instantly | Medium | Pass
TC-013 | SC-008 | UI to API consistency | User logged in | 1.Create note in UI 2.Validate through API | Created note available in API | Created note available in API | High | Pass
TC-014 | SC-008 | API to UI delete synchronization | User logged in | 1.Delete note via API 2.Refresh UI | Deleted note removed from UI | Deleted note removed from UI | High | Pass
TC-015 | SC-008 | Full end-to-end validation | User logged in | 1.Create note 2.Validate via API 3.Delete via API | Complete flow successful | Complete flow successful | High | Pass
TC-016 | SC-009 | API response time validation | API endpoint accessible | 1.Send GET request 2.Measure response time | API response time within acceptable limit | API response time within acceptable limit | Medium | Pass
TC-016 | SC-001 | Logout functionality | User logged in | 1.Click Logout | User logged out successfully | User logged out successfully | Medium | Pass

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User | Username: yashwanthveeraboina3015@gmail.com, Password: yashwanth3015 | Valid login scenarios
TD-002 | Invalid Username | wrong@mail.com | Used for invalid username validation
TD-003 | Invalid Password | wrong123 | Used for invalid password validation
TD-004 | Empty fields | Username: "" Password: "" | Used for empty username and empty password validation
TD-005 | Valid Note Title | API Testing Note | Used for valid note creation
TD-006 | Valid Note Description | This is sample note description | Used for valid note description input
TD-007 | Empty Note Title | "" | Used for empty note title validation
TD-008 | API Auth Token | aa87c4d13a6e46958a9b38f28af8dfa305c164335c1c46f6ab29e2d0a64f8e09 | Used for authenticated API requests
TD-009 | Invalid API Token | InvalidToken123 | Used for unauthorized API access validation
TD-010 | GET Notes Endpoint | /notes | Used for GET notes API validation
TD-011 | Hybrid Test Data | This is a full cycle test | Used for UI + API synchronization
TD-012 | API Response Data | {"title":"Sync Test","description":"API Sync Validation"} | Used for API response comparison validation
TD-013 | API Response Time Threshold | 2 Seconds | Used for API performance validation
TD-014 | Deleted Note Data | Deleted Note Title | Used for API to UI synchronization validation
TD-015 | Sample Unauthorized Request | GET /notes without token | Used for unauthorized access testing

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-001 | Cycle-1 | Login with valid credentials | QA-User1 | 2024-05-06 | Pass |  | User logged in successfully
TC-002 | Cycle-1 | Login with invalid username | QA-User1 | 2024-05-06 | Pass |  | Proper error message displayed
TC-003 | Cycle-1 | Login with invalid password | QA-User1 | 2024-05-06 | Pass |  | Proper error message displayed
TC-004 | Cycle-1 | Login with empty fields | QA-User1 | 2024-05-06 | Pass |  | Validation messages displayed correctly
TC-005 | Cycle-1 | Create note with valid details | QA-User1 | 2024-05-06 | Pass |  | Note created successfully
TC-006 | Cycle-1 | Validate instant note display in UI | QA-User1 | 2024-05-06 | Fail | DEF-001 | Note appearance delayed by few seconds after creation
TC-007 | Cycle-1 | Create note with empty title | QA-User1 | 2024-05-06 | Pass |  | Validation message displayed
TC-008 | Cycle-1 | Duplicate note creation validation | QA-User1 | 2024-05-06 | Pass |  | Duplicate note handled correctly
TC-009 | Cycle-1 | Invalid category validation | QA-User1 | 2024-05-06 | Pass |  | Invalid category handled successfully
TC-010 | Cycle-1 | Validate GET /notes API | QA-User1 | 2024-05-06 | Pass |  | Notes list returned successfully
TC-011 | Cycle-1 | Validate unauthorized API access | QA-User1 | 2024-05-06 | Pass |  | Unauthorized access blocked correctly
TC-012 | Cycle-1 | Validate invalid API token | QA-User1 | 2024-05-06 | Pass |  | Unauthorized response returned
TC-013 | Cycle-1 | Validate API response data | QA-User1 | 2024-05-06 | Pass |  | API returned accurate note data
TC-014 | Cycle-1 | Validate UI to API synchronization | QA-User1 | 2024-05-06 | Pass |  | UI and API synchronized correctly
TC-015 | Cycle-1 | Validate API to UI synchronization | QA-User1 | 2024-05-06 | Fail | DEF-002 | Deleted note remained visible until page refresh
TC-016 | Cycle-1 | Validate API response performance | QA-User1 | 2024-05-06 | Pass |  | API response time within acceptable limit
TC-017 | Cycle-1 | Logout functionality | QA-User1 | 2026-05-06 | Pass |  | User logged out successfully

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
FR-01 | TC-001, TC-002 | Login functionality | Covered | Complete
FR-02 | TC-003, TC-004, TC-005, TC-006 | Note creation and validation | Covered | Complete
FR-03 | TC-007, TC-008, TC-009, TC-010, TC-011,TC-016 | API functionality | Covered | Complete
FR-04 | TC-012 | Instant note visibility | Covered | Complete
FR-05 | TC-013, TC-014, TC-015 | Hybrid UI + API synchronization | Covered | Complete
FR-06 | TC-017 | Logout functionality | Covered | Complete

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-006 | Delay in instant note visibilit | Newly created note takes few seconds to appear in UI after creation | Low | Medium | Resloved | Dev-User1 | 2025-05-06 | Newly created note not reflected immediately in UI
DEF-002 | TC-015 | Deleted note refresh issue | Deleted note remains visible in UI until page refresh in some executions | Low | Medium | Resloved | Dev-User2 | 2025-05-06 | UI required manual refresh after note deletion

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name: | UI + API Hybrid Automation – ExpandTesting Notes App
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By: | V.Yashwanth Kumar
EXECUTION SUMMARY
Total Test Cases: | 17
Test Cases Executed: | 17
Test Cases Passed: | 17
Test Cases Failed: | 0
Pass Percentage: | 100
DEFECT SUMMARY
Total Defects: | 2
Critical Defects: | 0
High Defects: | 0
Medium Defects: | 2
Low Defects: | 0
Open Defects: | 0
Closed Defects: | 2
CONCLUSION
Testing Status: | Completed
Release Readiness: | Ready for deployment
Overall Recommendation: | Application is stable and functioning as expected
REMARKS
All test cases executed successfully without defects.